## Schedule
Task# | Description | Start Date | End Date | Duration in Days | Days Passed | Days Left | Effort Hours Estimate | Effort Hours Complete | Effort Hours Left | Input | Output | Responsible | Status
| Total --> |  |  | 826 | 71 | 0 | 755.5 | 710.5 | 0
001 | Project Start and End Dates | 2022-02-04 | 2022-04-16 | 71
002a | Maintaining the Project Schedule | 2022-02-04 | 2022-04-16 | 71 |  |  | 7 | 7 | 0 | Schedule-Team4 | Team Schedule Filled in | Chase | Complete
002b | Have team members update schedule | 2022-02-04 | 2022-04-16 | 71 |  |  | 3 | 3 | 0 | Schedule-Team4 | Team Members input time spent | Cole, Austin, Cade | Complete
003a | Populate the Jira roadmap | 2022-02-07 | 2022-02-16 | 9 |  |  | 4 | 4 | 0 | Jira | Jira Populated and Maintained | Chase | Complete
003b | Set up Chase with Jira | 2022-02-07 | 2022-02-16 | 9 |  |  | 0.75 | 0.75 | 0 | Jira | Chase Understands Jira | Chase | Complete
003c | Set up Austin with jira | 2022-02-07 | 2022-02-16 | 9 |  |  | 0.75 | 0.75 | 0 | Jira | Austin Understands Jira | Austin | Complete
003d | Set up Cade with Jira | 2022-02-07 | 2022-02-16 | 9 |  |  | 0.75 | 0.75 | 0 | Jira | Cade Understands Jira | Cade | Complete
003e | Set up Cole with Jira | 2022-02-07 | 2022-02-16 | 9 |  |  | 0.75 | 0.75 | 0 | Jira | Cole Understands Jira | Cole | Complete
004a | Create Team Github Repository | 2022-02-14 | 2022-02-20 | 6 |  |  | 2 | 2 | 0 | Github | Fully designed Github Repo | Chase | Complete
004b | Create and install Chase's GitHub | 2022-02-14 | 2022-02-20 | 6 |  |  | 0.5 | 0.5 | 0 | Github | Chase Understands Github | Chase | Complete
004c | Create and install Austin's GitHub | 2022-02-14 | 2022-02-20 | 6 |  |  | 0.5 | 0.5 | 0 | Github | Austin Understands Github | Austin | Complete
004d | Create and install Cade's GitHub | 2022-02-14 | 2022-02-20 | 6 |  |  | 0.5 | 0.5 | 0 | Github | Cade Understands Github | Cade | Complete
004e | Create and install Cole's GitHub | 2022-02-14 | 2022-02-20 | 6 |  |  | 0.5 | 0.5 | 0 | Github | Cole Understands Github | Cole | Complete
005a | Austin's VM Running | 2022-02-15 | 2022-03-01 | 14 |  |  | 1 | 1 | 0 | VirtualBox | Austin has VirtualBox Running | Austin | Complete
005b | Get Cole's VM Running | 2022-02-15 | 2022-03-01 | 14 |  |  | 1.5 | 1.5 | 0 | Virtual Box | Cole has Virtual Box Running | Cole | Complete
005c | Get Cade's VM Running | 2022-02-15 | 2022-03-01 | 14 |  |  | 5 | 5 | 0 | VirtualBox | Cade decided to group up | Cade | Complete
005d | Get Chase's VM Running | 2022-02-15 | 2022-03-01 | 14 |  |  | 2.5 | 2.5 | 0 | Virtual Box | Chase working on home env | Chase | Complete
006a | Get Chase's Installation is running | 2022-02-15 | 2022-03-01 | 14 |  |  | 4 | 4 | 0 | Source Instalation Instructions | Chase can work on Project | Chase | Complete
006b | Get Austin's Installation is running | 2022-02-15 | 2022-03-01 | 14 |  |  | 3 | 3 | 0 | Source Instalation Instructions | Austin can work on Project | Austin | Complete
006c | Get Cade's Installation is running | 2022-02-15 | 2022-03-01 | 14 |  |  | 1.5 | 1.5 | 0 | Source Instalation Instructions | Cade can work on Project | Cade | Complete
006d | Get Cole's Installation is running | 2022-02-15 | 2022-03-01 | 14 |  |  | 3 | 3 | 0 | Source Instalation Instructions | Cole can work on Project | Cole | Complete
007a | Create MRI Tech Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 1.5 | 1.5 | 0 | Thoughts and Ideas of Others | MRI Tech.txt | Chase | Complete
007b | Create Ultrasound Tech Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 1.5 | 1.5 | 0 | Thoughts and Ideas of Others | Utrasound Tech.txt | Chase | Complete
007c | Create Front Desk Worker Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | Front Desk.txt | Austin | Complete
007d | Create Guest Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | Guest.txt | Austin | Complete
007e | Create Physician Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | Physician.txt | Cade | Complete
007f | Create IT Department Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | IT Department.txt | Cade | Complete
007g | Create Radiologist Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | Radiologist.txt | Cole | Complete
007h | Create Transporter Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | Transporter.txt | Cole | Complete
008a | Chase Thinks of Features | 2022-02-12 | 2022-03-03 | 19 |  |  | 1 | 1 | 0 | Ideas of Features | Feature Discription in Github | Chase | Complete
008b | Austin Thinks of Features | 2022-02-12 | 2022-03-03 | 19 |  |  | 1 | 1 | 0 | Ideas of Features | Feature Discription in Github | Austin | Complete
008c | Cade Thinks of Features | 2022-02-12 | 2022-03-03 | 19 |  |  | 1 | 1 | 0 | Ideas of Features | Feature Discription in Github | Cade | Complete
008d | Cole Thinks of Features | 2022-02-12 | 2022-03-03 | 19 |  |  | 1 | 1 | 0 | Ideas of Features | Feature Discription in Github | Cole | Complete
009a | Study the System architecture | 2022-02-19 | 2022-03-03 | 12 |  |  | 2 | 2 | 0 | Source Project Architecture | System Architecture Learned | Chase, Austin, Cole, Cade | Complete
009b | Study the webpages layout | 2022-02-19 | 2022-03-03 | 12 |  |  | 6 | 6 | 0 | Loaded Source Application GUI | Web functionality Learned | Chase, Austin, Cole, Cade | Complete
009c | Study the CSS behind the webpage | 2022-02-19 | 2022-03-03 | 12 |  |  | 4 | 4 | 0 | Source CSS file | CSS formating understood | Chase, Austin, Cole, Cade | Complete
009d | Study the HTML | 2022-02-19 | 2022-03-03 | 12 |  |  | 10 | 10 | 0 | Source HTML files | HTML to be converted learned | Chase, Austin, Cole, Cade | Complete
009e | Study the Database architecture | 2022-02-19 | 2022-03-03 | 12 |  |  | 6 | 6 | 0 | Source Databse Architecture | Database Requirments learned | Chase, Austin, Cole, Cade | Complete
010a | Chase learns JavaFX & watches tutorial | 2022-03-01 | 2022-03-06 | 5 |  |  | 4 | 4 | 0 | JavaFX GUI Course ☕ | Chase has learned JavaFX | Chase | Complete
010b | Austin learns JavaFX & watches tutorial | 2022-03-01 | 2022-03-06 | 5 |  |  | 4 | 4 | 0 | JavaFX GUI Course ☕ | Austin has learned JavaFX | Austin | Complete
010c | Cade learns JavaFX & watches tutorial | 2022-03-01 | 2022-03-06 | 5 |  |  | 4 | 4 | 0 | JavaFX GUI Course ☕ | Cade has learned JavaFX | Cade | Complete
010d | Cole learns JavaFX & watches tutorial | 2022-03-01 | 2022-03-06 | 5 |  |  | 4 | 4 | 0 | JavaFX GUI Course ☕ | Cole has learned JavaFX | Cole | Complete
010e | Chase installed JavaFX in enviroment | 2022-03-01 | 2022-03-05 | 4 |  |  | 0.25 | 0.25 | 0 | Java Extension Pack | Chase can use JavaFX | Chase | Complete
010f | Austin installed JavaFX in enviroment | 2022-03-01 | 2022-03-05 | 4 |  |  | 0.25 | 0.25 | 0 | Java Extension Pack | Austin can use JavaFX | Austin | Complete
010g | Cade installed JavaFX in enviroment | 2022-03-01 | 2022-03-05 | 4 |  |  | 0.25 | 0.25 | 0 | Java Extension Pack | Cade can use JavaFX | Cade | Complete
010h | Cole installed JavaFX in enviroment | 2022-03-01 | 2022-03-05 | 4 |  |  | 0.25 | 0.25 | 0 | Java Extension Pack | Cole can use JavaFX | Cole | Complete
011a | Convert Webapp to Desktop App | 2022-03-06 | 2022-03-21 | 15 |  |  | 32 | 32 | 0 | Source HTML files |  | Chase, Cole, Austin, Cade | Complete
012a | Creating Home FXML | 2022-03-06 | 2022-03-15 | 9 |  |  | 7 | 7 | 0 | RIS System | Beginning of Project | Chase | Complete
012b | Create FX Enviroment | 2022-03-06 | 2022-03-15 | 9 |  |  | 3 | 3 | 0 | RIS System | Visual Start of Project | Chase | Complete
012c | Create Springboot enviroment | 2022-03-08 | 2022-03-12 | 4 |  |  | 1 | 1 | 0 | RIS System | Launch Program Created | Chase | Complete
012d | Create base events | 2022-03-10 | 2022-03-11 | 1 |  |  | 1 | 1 | 0 | RIS System | Event Handlers Created | Chase, Austin, Cole, Cade | Complete
012e | Get Login Functionality Working | 2022-03-11 | 2022-03-17 | 6 |  |  | 5 | 5 | 0 | RIS System | Login Screen Working Functionally and Visually | Chase, Cole | Complete
012f | Create Export for SQL Database | 2022-03-05 | 2022-03-06 | 1 |  |  | 2 | 2 | 0 | RIS System | Database Maitnance Started | Cole, Chase | Complete
013 | Add Functionality to the Admin User |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Complete
013a | Austin creating admin user | 2022-03-09 | 2022-03-20 | 11 |  |  | 96 | 96 | 0 | VS code | Admin page functional | Austin | Complete
013b | Cole creating admin user | 2022-03-09 | 2022-03-20 | 11 |  |  | 119 | 119 | 0 | VS code | Admin page functional | Cole | Complete
013c | Cade creating admin user | 2022-03-09 | 2022-03-20 | 11 |  |  | 81 | 81 | 0 | VS code | Admin page functional | Cade | Complete
013d | Chase creating admin user | 2022-03-09 | 2022-03-20 | 11 |  |  | 123 | 123 | 0 | VS code | Admin page functional | Chase | Complete
014 | Fixing Doc user login | 2022-03-11 | 2022-03-13 | 2 |  |  | 7 | 7 | 0 | VS code | Fixed Doc User Original system | Cole | Complete
015 | Creating other user pages | 2022-03-21 | 2022-03-22 | 1 |  |  | 8 | 8 | 0 | VS code | Additional user now function | Chase, Austin, Cole, Cade | Complete
016 | Debug the RIS |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Complete
016a | Chase debugging system | 2022-03-22 | 2022-03-24 | 2 |  |  | 15 | 15 | 0 | VS code | Majority of bugs repaired | Chase | Complete
016b | Cole debugging system | 2022-03-22 | 2022-03-24 | 2 |  |  | 15 | 15 | 0 | VS code | Majority of bugs repaired | Cole | Complete
016c | Cade debugging system | 2022-03-22 | 2022-03-24 | 2 |  |  | 15 | 15 | 0 | VS code | Majority of bugs repaired | Cade | Complete
016d | Austin debugging system | 2022-03-22 | 2022-03-24 | 2 |  |  | 15 | 15 | 0 | VS code | Majority of bugs repaired | Austin | Complete
017 | Implement Feature 1 |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Complete
017a | Create Show Patient Alert Button | 2022-03-24 | 2022-03-28 | 4 |  |  | 3 | 3 | 0 | VS code | Usable Alerts Button | Chase | Complete
017b | Populate Show Patient Alert Table with the Paitent's Alerts | 2022-03-28 | 2022-04-02 | 5 |  |  | 5 | 5 | 0 | VS code | Table Shows Patients Alerts Button | Chase | Complete
017c | Add Patient Alerts Button to Required Sections | 2022-04-02 | 2022-04-03 | 1 |  |  | 3 | 3 | 0 | VS code | Required Areas have Different Patients Alerts Button | Chase, Cole | Complete
017d | Update Create/Modify Patient Queries to Insert Patient's Alerts | 2022-04-02 | 2022-04-03 | 1 |  |  | 2 | 2 | 0 | VS code | Working Queries | Cole | Complete
017e | Add ListView to Create/Modify Patients with Alert Options | 2022-04-03 | 2022-04-06 | 3 |  |  | 4 | 4 | 0 | VS code | Visual Graphic for Adding Patient Alert | Chase | Complete
018 | Add Final Doc User Functionallity |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Complete
018a | Add Completed/Closed Orders Tables | 2022-03-24 | 2022-03-27 | 3 |  |  | 2 | 2 | 0 | VS code | Table Appears on Home Screen | Chase | Complete
018b | Add Query and Constructor to Populate Completed/Closed Orders Tables | 2022-03-27 | 2022-03-28 | 1 |  |  | 2 | 2 | 0 | VS code | Functional Completed/Closed Orders Tables | Chase, Cole | Complete
018c | Upate Completed/Review Imaging Orders Insert Queries to update Order Status | 2022-03-28 | 2022-03-29 | 1 |  |  | 1 | 1 | 0 | VS code | Queries for Tables now Move Orders Along as Processed By User | Chase, Cole | Complete
018d | Update Create Order to Autofill Order Status | 2022-03-29 | 2022-03-31 | 2 |  |  | 1 | 1 | 0 | VS code | Less User Input into System and less complexity | Chase | Complete
019 | Add Show Image Button to RIS |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Complete
019a | Create Show Image Button to show Current Orders Image | 2022-03-24 | 2022-03-27 | 3 |  |  | 3 | 3 | 0 | VS code | Working Show Image Button with Parameters | Cole | Complete
019b | Add Show Image Button to Required Sections | 2022-03-27 | 2022-03-28 | 1 |  |  | 2 | 2 | 0 | VS code | Show Image Button Appears on Sections where Required | Cole, Chase | Complete
020 | Add Hostside Encryption |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Complete
020a | Add Encrypt/Decrypt Class | 2022-03-24 | 2022-03-31 | 7 |  |  | 1 | 1 | 0 | VS code | Encrypt/Decrypt Class created | Austin | Complete
020b | Add Class Usage to RIS | 2022-03-31 | 2022-04-03 | 3 |  |  | 4 | 4 | 0 | Encrypt/Decrypt Class | Encrypt/Decrypt Class Functional inside the RIS | Austin, Chase | Complete
021 | Create and Connect RIS to Remote Database |  |  | 0 |  |  | 0 | 0 | 0 |  |  | Cade | Complete
021a | Create Remote MySQL Datbase | 2022-03-24 | 2022-04-07 | 14 |  |  | 2 | 2 | 0 | Google Cloud, Amazon Web Services | Running Remote Database | Cade | Complete
021b | Connect Remote Datbase to local RIS | 2022-03-24 | 2022-04-07 | 14 |  |  | 14 | 14 | 0 | Remote Database | Working Remote Connection to Database | Cade. Chase. Cole | Complete
022 | Fix Visual Appearance of the Project | 2022-04-05 | 2022-04-07 | 2 |  |  | 0 | 0 | 0 |  |  |  | Complete
022a | Immplement Consistent Font Size and Style | 2022-04-05 | 2022-04-07 | 2 |  |  | 1 | 1 | 0 | RIS System | Increased Visual Consistency in RIS | Chase | Complete
022b | Immplement Consistent Layout Pane Positioning and Size | 2022-04-05 | 2022-04-07 | 2 |  |  | 2 | 2 | 0 | RIS System | Increased Visual Consistency in RIS | Chase | Complete
022c | Add Button and Feature Consistency to Different User Portals | 2022-04-04 | 2022-04-07 | 3 |  |  | 3 | 3 | 0 | RIS System | Increased Visual Consistency in RIS | Chase, Cole | Complete
023 | Clean-up Code Logic and Fix Errors | 2022-04-03 | 2022-04-08 | 5 |  | 0 | 0 | 0 | 0 |  |  |  | Complete
023a | Add .trim() to the RIS System | 2022-04-03 | 2022-04-06 | 3 |  |  | 1 | 1 | 0 | RIS System | RIS Stystem Without Insert Errors | Chase, Cole | Complete
024 | Implement Feature 2 |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  | Complete
024a | Create Add Consent Form Page | 2022-04-06 | 2022-04-09 | 3 |  |  | 0 | 0 | 0 | RIS System | Visual Consent Form Page | Cole | Complete
024b | Add Table for Consent Forms in Database | 2022-04-06 | 2022-04-09 | 3 |  |  | 1 | 1 | 0 | Local Database | New Database Table | Cole | Complete
024c | Insert Consent Form Page into the RIS | 2022-04-06 | 2022-04-09 | 3 |  |  | 5 | 5 | 0 | RIS System | RIS with Feature 2 Implemented | Cole | Complete
024d | Test Feature 2 Implementation | 2022-04-06 | 2022-04-09 | 3 |  |  | 1 | 1 | 0 | RIS System with Feature 2 | Completion of Feature 2 Implementation | Cole | Complete
025a | Clean Up Doc User Files | 2022-04-06 | 2022-04-09 | 3 |  |  | 2 | 2 | 0 | Doc User Files | Doc Files without Errors | Chase | Complete
025b | Clean Up Tech User Files | 2022-04-06 | 2022-04-09 | 3 |  |  | 3 | 3 | 0 | Tech User Files | Tech Files without Errors | Chase, Cole | Complete
025c | Clean Up Admin User Files | 2022-04-06 | 2022-04-09 | 3 |  |  | 1 | 1 | 0 | Admin User Files | Admin Files without Errors | Chase | Complete
025d | Clean Up User User Files | 2022-04-06 | 2022-04-09 | 3 |  |  | 1 | 1 | 0 | User User Files | User Files without Errors | Chase | Complete
025e | Clean Up Desk User Files | 2022-04-06 | 2022-04-09 | 3 |  |  | 1 | 1 | 0 | Desk User Files | Desk Files without Errors | Chase | Complete
025f | Clean Up Radio User Files | 2022-04-06 | 2022-04-09 | 3 |  |  | 1 | 1 | 0 | Radio User Files | Radio Files without Errors | Chase | Complete
026 | Implement Feature 3 |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  |  | Rows after this don’t appear to be working
026a | Create Button to Open Medical History | 2022-04-13 | 2022-04-15 | 2 |  |  | 1 | 1 | 0 | Feature 3 Requirments | Visual Button | Austin | Complete
026b | Import Table Logic into Medical History | 2022-04-13 | 2022-04-15 | 2 |  |  | 6 | 6 | 0 | Feature 3 Requirments | Working Table for Medical History | Austin, Chase | Complete
026c | Create Table Controller | 2022-04-13 | 2022-04-15 | 2 |  |  | 2 | 2 | 0 | Feature 3 Requirments | Table Controller Duplicated | Austin | Complete
026d | Fix Appearance of Medical History Page | 2022-04-13 | 2022-04-15 | 2 |  |  | 2 | 2 | 0 | Feature 3 Requirments |  | Austin | Complete
026e | Implement Feature 3 into the RIS | 2022-04-13 | 2022-04-15 | 2 |  |  | 1 | 1 | 0 | Feature 3 |  | Chase | Complete
026f | Test RIS with Feature 3 Implemented | 2022-04-13 | 2022-04-15 | 2 |  |  | 1 | 1 | 0 | Implemented Feature 3 | New Radiology System | Chase, Cole | Complete
027 | Create Database Setup Instructions | 2022-04-14 | 2022-04-15 | 1 |  |  | 1 | 1 | 0 |  |  | Cade | Complete
028 | Create RIS User Manual | 2022-04-15 | 2022-04-16 | 1 |  |  | 2 | 2 | 0 |  |  | Chase | Complete
Complete
029 | Create List of Requirments | 2022-04-14 | 2022-04-15 | 1 |  |  | 1 | 1 | 0 |  |  | Cade, Austin | Complete
030 | Create Diagrams | 2022-04-14 | 2022-04-16 | 1 |  |  | 0 | 0 | 0 |  |  |  | Complete
030a | Create System Models | 2022-04-14 | 2022-04-15 | 1 |  |  | 3 | 3 | 0 |  |  | Cole | Complete
030b | Create DatabaseERD | 2022-04-14 | 2022-04-15 | 1 |  |  | 3 | 3 | 0 |  |  | Cole | Complete
030c | Create System Flow Chart | 2022-04-14 | 2022-04-15 | 1 |  |  | 3 | 3 | 0 |  |  | Cole | Complete
030d | Create System Archetecture | 2022-04-14 | 2022-04-15 | 1 |  |  | 3 | 3 | 0 |  |  | Cole | Complete
031 | Create Test Cases | 2022-04-14 | 2022-04-14 | 0 |  |  | 1 | 1 | 0 |  |  | Cole | Complete
032 | Test Test Cases | 2022-04-14 | 2022-04-14 | 0 |  |  | 3 | 3 | 0 |  |  | Cole | Complete
033 | Create Tools Used | 2022-04-16 | 2022-04-16 | 0 |  |  | 1 | 1 | 0 |  |  | Austin, Cade | Complete
034 | Organize Minutes and Status Reporst | 2022-04-16 | 2022-04-16 | 0 |  |  | 1 | 1 | 0 |  |  | Chase | Complete
035 | Test Installation Instructions | 2022-04-15 | 2022-04-16 | 1 |  |  | 3 | 3 | 0 |  |  | Austin, Cade | Complete
036 | Create Lessons Learned | 2022-04-15 | 2022-04-16 | 1 |  |  | 1 | 1 | 0 | Experiances and Status Reports |  | Cade | Complete
037 | Create Table of Contents | 2022-04-16 | 2022-04-16 | 0 |  |  | 1 | 1 | 0 | Project Deliverables | Contents of Project | Austin, Cade | Complete
038 | Create PowerPoint Presenation | 2022-04-16 | 2022-04-16 | 0 |  |  | 1 | 1 | 0 | Project Deliverables | Presentation of Project | Chase | Complete
Formulas:
Days Passed = TODAY() -[Start Date, row below]
Days Left = [End Date, row below]-TODAY()