## Schedule
Task# | Description | Start Date | End Date | Duration in Days | Days Passed | Days Left | Effort Hours Estimate | Effort Hours Complete | Effort Hours Left | Input | Output | Responsible | Status
| Total --> |  |  | 645 | 47 | 24 | 142.5 | 82.5 | 60
001 | Project Start and End Dates | 2022-02-04 | 2022-04-16 | 71
002a | Maintaining the System Schedule | 2022-02-04 | 2022-04-16 | 71 |  |  | 4 | 2 | 2 | Schedule-Team4 | Team Schedule Filled in | Chase | In Progress
002b | Have team members update schedule | 2022-02-04 | 2022-04-16 | 71 |  |  | 3 | 0.5 | 2.5 | Schedule-Team4 | Team Members input time spent | Cole, Austin, Cade | In Progress
003a | Populate the Jira roadmap | 2022-02-07 | 2022-02-16 | 9 |  |  | 4 | 2.5 | 1.5 | Jira | Jira Populated and Maintained | Chase | In Progress
003b | Set up Chase with Jira | 2022-02-07 | 2022-02-16 | 9 |  |  | 0.75 | 0.75 | 0 | Jira | Chase Understands Jira | Chase | Complete
003c | Set up Austin with jira | 2022-02-07 | 2022-02-16 | 9 |  |  | 0.75 | 0.75 | 0 | Jira | Austin Understands Jira | Austin | Complete
003d | Set up Cade with Jira | 2022-02-07 | 2022-02-16 | 9 |  |  | 0.75 | 0.75 | 0 | Jira | Cade Understands Jira | Cade | Complete
003e | Set up Cole with Jira | 2022-02-07 | 2022-02-16 | 9 |  |  | 0.75 | 0.75 | 0 | Jira | Cole Understands Jira | Cole | Complete
004a | Create Team Github Repository | 2022-02-14 | 2022-02-20 | 6 |  |  | 2 | 2 | 0 | Github | Fully designed Github Repo | Chase | Complete
004b | Create and install Chase's GitHub | 2022-02-14 | 2022-02-20 | 6 |  |  | 0.5 | 0.5 | 0 | Github | Chase Understands Github | Chase | Complete
004c | Create and install Austin's GitHub | 2022-02-14 | 2022-02-20 | 6 |  |  | 0.5 | 0.5 | 0 | Github | Austin Understands Github | Austin | Complete
004d | Create and install Cade's GitHub | 2022-02-14 | 2022-02-20 | 6 |  |  | 0.5 | 0.5 | 0 | Github | Cade Understands Github | Cade | Complete
004e | Create and install Cole's GitHub | 2022-02-14 | 2022-02-20 | 6 |  |  | 0.5 | 0.5 | 0 | Github | Cole Understands Github | Cole | Complete
005a | Austin's VM Running | 2022-02-15 | 2022-03-01 | 14 |  |  | 1 | 1 | 0 | VirtualBox | Austin has VirtualBox Running | Austin | Complete
005b | Get Cole's VM Running | 2022-02-15 | 2022-03-01 | 14 |  |  | 1.5 | 1.5 | 0 | Virtual Box | Cole has Virtual Box Running | Cole | Complete
005c | Get Cade's VM Running | 2022-02-15 | 2022-03-01 | 14 |  |  | 5 | 5 | 0 | VirtualBox | Cade decided to group up | Cade | Complete
005d | Get Chase's VM Running | 2022-02-15 | 2022-03-01 | 14 |  |  | 2.5 | 2.5 | 0 | Virtual Box | Chase working on home env | Chase | Complete
006a | Get Chase's Installation is running | 2022-02-15 | 2022-03-01 | 14 |  |  | 4 | 4 | 0 | Source Instalation Instructions | Chase can work on Project | Chase | Complete
006b | Get Austin's Installation is running | 2022-02-15 | 2022-03-01 | 14 |  |  | 3 | 3 | 0 | Source Instalation Instructions | Austin can work on Project | Austin | Complete
006c | Get Cade's Installation is running | 2022-02-15 | 2022-03-01 | 14 |  |  | 1.5 | 1.5 | 0 | Source Instalation Instructions | Cade can work on Project | Cade | Complete
006d | Get Cole's Installation is running | 2022-02-15 | 2022-03-01 | 14 |  |  | 3 | 3 | 0 | Source Instalation Instructions | Cole can work on Project | Cole | Complete
007a | Create MRI Tech Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 1.5 | 1.5 | 0 | Thoughts and Ideas of Others | MRI Tech.txt | Chase | Complete
007b | Create Ultrasound Tech Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 1.5 | 1.5 | 0 | Thoughts and Ideas of Others | Utrasound Tech.txt | Chase | Complete
007c | Create Front Desk Worker Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | Front Desk.txt | Austin | Complete
007d | Create Guest Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | Guest.txt | Austin | Complete
007e | Create Physician Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | Physician.txt | Cade | Complete
007f | Create IT Department Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | IT Department.txt | Cade | Complete
007g | Create Radiologist Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | Radiologist.txt | Cole | Complete
007h | Create Transporter Persona | 2022-02-12 | 2022-02-19 | 7 |  |  | 0.5 | 0.5 | 0 | Thoughts and Ideas | Transporter.txt | Cole | Complete
008a | Chase Thinks of Features | 2022-02-12 | 2022-03-03 | 19 |  |  | 1 | 1 | 0 | Ideas of Features | Feature Discription in Github | Chase | Complete
008b | Austin Thinks of Features | 2022-02-12 | 2022-03-03 | 19 |  |  | 1 | 1 | 0 | Ideas of Features | Feature Discription in Github | Austin | Complete
008c | Cade Thinks of Features | 2022-02-12 | 2022-03-03 | 19 |  |  | 1 | 1 | 0 | Ideas of Features | Feature Discription in Github | Cade | Complete
008d | Cole Thinks of Features | 2022-02-12 | 2022-03-03 | 19 |  |  | 1 | 1 | 0 | Ideas of Features | Feature Discription in Github | Cole | Complete
009a | Study the System architecture | 2022-02-19 | 2022-03-03 | 12 |  |  | 2 | 0 | 2 | Source Project Architecture | System Architecture Learned | Chase, Austin, Cole, Cade | In Progress
009b | Study the webpages layout | 2022-02-19 | 2022-03-03 | 12 |  |  | 6 | 3 | 3 | Loaded Source Application GUI | Web functionality Learned | Chase, Austin, Cole, Cade | In Progress
009c | Study the CSS behind the webpage | 2022-02-19 | 2022-03-03 | 12 |  |  | 4 | 1 | 3 | Source CSS file | CSS formating understood | Chase, Austin, Cole, Cade | In Progress
009d | Study the HTML | 2022-02-19 | 2022-03-03 | 12 |  |  | 10 | 2 | 8 | Source HTML files | HTML to be converted learned | Chase, Austin, Cole, Cade | In Progress
009e | Study the Database architecture | 2022-02-19 | 2022-03-03 | 12 |  |  | 6 | 0 | 6 | Source Databse Architecture | Database Requirments learned | Chase, Austin, Cole, Cade | In Progress
010a | Chase learns JavaFX & watches tutorial | 2022-03-01 | 2022-03-06 | 5 |  |  | 4 | 4 | 0 | JavaFX GUI Course ☕ | Chase has learned JavaFX | Chase | Complete
010b | Austin learns JavaFX & watches tutorial | 2022-03-01 | 2022-03-06 | 5 |  |  | 4 | 4 | 0 | JavaFX GUI Course ☕ | Austin has learned JavaFX | Austin | Complete
010c | Cade learns JavaFX & watches tutorial | 2022-03-01 | 2022-03-06 | 5 |  |  | 4 | 4 | 0 | JavaFX GUI Course ☕ | Cade has learned JavaFX | Cade | Complete
010d | Cole learns JavaFX & watches tutorial | 2022-03-01 | 2022-03-06 | 5 |  |  | 4 | 4 | 0 | JavaFX GUI Course ☕ | Cole has learned JavaFX | Cole | Complete
010e | Chase installed JavaFX in enviroment | 2022-03-01 | 2022-03-05 | 4 |  |  | 0.25 | 0.25 | 0 | Java Extension Pack | Chase can use JavaFX | Chase | Complete
010f | Austin installed JavaFX in enviroment | 2022-03-01 | 2022-03-05 | 4 |  |  | 0.25 | 0.25 | 0 | Java Extension Pack | Austin can use JavaFX | Austin | Complete
010g | Cade installed JavaFX in enviroment | 2022-03-01 | 2022-03-05 | 4 |  |  | 0.25 | 0.25 | 0 | Java Extension Pack | Cade can use JavaFX | Cade | Complete
010h | Cole installed JavaFX in enviroment | 2022-03-01 | 2022-03-05 | 4 |  |  | 0.25 | 0.25 | 0 | Java Extension Pack | Cole can use JavaFX | Cole | Complete
011a | Convert Webapp to Desktop App | 2022-03-06 | 2022-03-21 | 15 |  |  | 32 | 0 | 32 | Source HTML files |  | TBD | In Progress
012a | Creating Home FXML |  |  | 0 |  |  | 7 | 7 | 0 |  |  | Chase | Complete
| Create FX Enviroment |  |  | 0 |  |  |  |  | 0
| Create Springboot enviroment |  |  | 0 |  |  |  |  | 0
| Create base events |  |  | 0 |  |  |  |  | 0
| get login functionality working with SQL |  |  | 0 |  |  |  |  | 0 |  |  | TBD
| Create Export for SQL Database |  |  | 0 |  |  | 2 | 2 | 0 |  |  | Cole, Chase
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
| Fixing the Doc User Login | 2022-03-11 | 2022-03-13 | 2 |  |  | 7 | 7 | 0 |  | Fixed Doc User Origonal System | Cole
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 2022-03-09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
| Austin |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 8 | 10 | 8 | 8 | 10 | 10 | 10 | 6 | 5
| Cole |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 6 | 8 | 8 | 8 | 8 | 8 | 10 | 8 | 8 | 10 | 10 | 10 | 6 | 6
| Cade |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 6 | 8 | 0 | 8 | 0 | 8 | 10 | 8 | 8 | 10 | 10 | 0 | 6 | 6
| Chase |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 6 | 8 | 8 | 8 | 8 | 11 | 10 | 8 | 8 | 10 | 10 | 10 | 10 | 5 | 12
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
Formulas:
Days Passed = TODAY() -[Start Date, row below]
Days Left = [End Date, row below]-TODAY()